## Sheet1
Project name: Paint |  | Team number and members: 114, Joel Carlson, Ty Strayer
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date | Comments | Current Status
1 | Creates a blank work area and panels/buttons with no functionality. | Run Paint and a window will open. | 2008-04-07 | 2008-04-04 |  | End of Class 8-Apr: Currently planning on reorganizing how various classes interact.
2 | Clicking on the pencil tool and clicking and dragging in the work area will draw a line. | Run program, click pencil, try to draw line. | 2008-04-07 | 2008-04-07 |  | End of Class 10-Apr: Have the beginning workings of rectangle. Still need to restructure a lot of things.
3 | Clicking the brush tool and click-and-drag in work area draws brush line. | Run program, click brush tool, try to draw. | 2008-04-07 | 2008-04-08 |  | End of Class 11-Apr: Have almost all the basic things done except for picking a color not working completely correct.
4 | Clicking on a color in the palette sets that color as active. Future drawings will use that color. | Select various colors and try drawing different colored lines with pencil and brush. | 2008-04-07 | 2008-04-11 | Implemented after rectangle and oval because of change of mind in order.
5 | Clicking rectangle tool activates rectangle drawing. Clicking and dragging in window will construct a rectangle. | Run program, click rectangle tool, try to draw rectangle. | 2008-04-09 | 2008-04-10
6 | Clicking oval tool activates oval drawing. Clicking and dragging in window will construct an oval. | Run program, click oval tool, try to draw oval. | 2008-04-09 | 2008-04-11
7 | Clicking polygon tool activates polygon drawing. Mouse drags for first line. Then click subsequent points and new lines are attached to the last endpoint. | Run program, click polygon tool, try to draw various polygons. | 2008-04-09 | 2008-04-11 | Full functionality achieved 12-Apr
8 | Clicking paint bucket tool and clicking in workspace fills in the entire area encompassing the point the user clicked. | Run program. Try various fillings with rectangles, ovals, polygons, and free-hand objects. | 2008-04-11 |  | Did not do this.
9 | Clicking Color Picker and clicking on an area in the window makes that color active in the palette. | Try selecting various drawn objects of a color and make sure palette changes what color is selected. | 2008-04-11 |  | Did not do this.
10 | Add shift-key functionality to rectangle and oval (forces squares/circles). | Use rectangle and oval, hold shift-key, and assure that only squares and circles are formed. | 2008-04-11 | 2008-04-11 | Errors fixed 12-Apr
11 | Add eraser tool | Draw stuff and erase it. | 2008-04-11 | 2008-04-12
12 | Using rectangular select button and clicking and dragging a rectangle in window "selects" that area. User can then click and drag that to a different location in the work area. | Make a bunch of random drawings. Use rectangular select tool and move stuff around. | 2008-04-12 |  | Did not do this.
13 | Spray Paint | Draw graffiti. | 2008-04-12 | 2008-04-14
14 | Clicking "File" button opens file menu with no functionality. | Click "File" and assure that menu opens with new buttons. | 2008-04-13 | 2008-04-04 | Ended up getting done with main window
15 | In "File" - clicking "save as" brings up a save prompt. Will save as a JPEG. | Click "File" - "Save As" and try saving file. | 2008-04-13 | 2008-04-14
16 | In "File" - clicking "save" will prompt "save as" if never saved before, otherwise just saves. | Try saving on new file, and then saving again when already saved once. | 2008-04-13 | 2008-04-14
17 | In "File" - clicking "new" prompts if user really wants to start a new file (gives option to save as well). | Try saving file from here. Try creating new files. | 2008-04-13 | 2008-04-14
18 | In "File" - clicking "open" brings up prompt to locate a previous file. | Create and save a file. Close program. Reopen program. Try to open previous file. | 2008-04-13 | 2008-04-14 | User enters file name, rather than a window to navigate to file. Open doesn't work perfectly, but if you save, open a different picture, then reopen the first, the changes will be there.
19 | Edit Menu | Edit menu pops up with functionable undo option. | Time Permitting | 2008-04-14 | Added "redo" as well, with altered behavior in that it stores "undone" actions forever and can be "redone" at any point in future.
20 | Right-click Context Menu | Test it | Time Permitting |  | Did not do this.