## Sheet1
Project name: Java Paint |  | Team number and members: Jon Klein, Bryan Cobb, Team Number: 112
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date | Notes | Excuse
1 | Draw properly sized bottom and side panels,and drawable area. | Start up program, observe. See if panels are created. | April 9th | April 8th. | Now with correctly sized drawing panel!
2 | Fill panels side, and blank color buttons on bottom panel, also temporary labels for future context sensitive help or mouse location. | Start up program, observe. See if panels are filled. | April 9th | April 7th.
3 | Make buttons clickable, diagnostic output specific to each button on console. | Start up program and click buttons, observe console output. | April 9th | April 7th. | Still need to connect buttons to something useful.
4 | Single pixel paintbrush operational, selected from side panel. | Start up program and select paintbrush, click and click and drag on drawing area. | April 10th | April 10th | Lines are not drawn cleanly, but the small pencil tool works. Clicking paintbrush not needed, it is selected by default.
5 | Single pixel paintbrush, with color selection. | Start up program and select paintbrush and color. Click and click and drag on drawing area. | April 10th | April 12th | Late, color changing was more difficult than expected. | Done late, but the drawing panel is now aware of the currently selected color.
6 | Bottom panel will reflect mouse location in drawing area, be blank if out of area. | Wiggle mouse in and out of drawing area. | April 11th | April 10th | Completed a day early, instead of paintbrush. (reflects work done on connecting panels)
7 | Multi pixel brushes working, with color selection. | Start up program and select paintbrush and color, click and click and drag on drawing area. | April 11th | April 12th | Late, color changing was more difficult than expected. | Color changing took more work than expected.
8 | Line drawing in side panel, working with drawing area to create them. | Click line on side panel, click and drag on drawing area. | April 11th | April 10th | Completed early?
9 | Rectangle and circles in side panel, working with drawing area to create them. | Click rectangle on side panel, click and drag on drawing area. Click circle on side panel, click and drag on drawing area. | April 12th | April 10th | Completed early, will need to be updated when new color support is working.
10 | Rectangle and circles in side panel, working with drawing area and color selection, with filling secondary color. | Click rectangle on side panel. Click color selection. Click color filling. Click and drag on drawing area. Click circle on side panel, click and drag on drawing area. | April 12th | April 12th | Sorta working. Rectangles and circles work, but they currently must all either be filled or not filled. Support for mixed is not yet working.
11 | “Eraser” working, secondary color multipixel paintbrush. | Select secondary color on bottom panel. Click eraser on side panel. Erase drawn objects with brush. | April 12th | April 12th | Select secondary/fill color by selecting color on bottom panel then clicking fill button.
12 | Bucket fill button, fills rectangles with default color. | Create rectangle, fill with default color. Fill entire drawing area. | April 13th |  | Shapes are fillable at construction, but not by fill tool.
13 | Bucket fill button, works with ovals and line drawn shapes. | Draw oval, fill with default color. Draw shape out of lines, fill with default color. | April 13th |  | We decided against doing bucket fill, and came up with new extra features.
14 | Bucket fill button, works with freeform drawn shapes and multiple colors. | Draw freeform shape, fill with blue. | April 14th
15 | Polygon in side panel, working in drawing area with color selection. | Select polygon. Click on drawing area. Click mouse to other spots on drawing area. Right click to connect final line with starting point | April 13th. | April 14th | Late. Partially functional polygon by IEP date, however, bugfixing lasted until the 14th.
16 | Constrained ovals and rectangles into circles and squares, using keyboard key 'shift'. | Select rectangle, press shift, draw rectangle on drawing area. Select circle, press shift, draw rectangle on drawing area. | April 14th | April 14th | A little less fluid than normal drawing.
17
18 | Extra features added beyond the original IEP. | How to demonstrate it:
19 | Save/load, with fancy dialog box. | Draw, click save, save to file (.png appended automatically). Click load, profit? |  | April 13th
20 | Text fields, with color selection. | Click text button, click on drawing panel. Select color on bottom panel. |  | April 12th
21 | UI enhancements: buttons depress, background color set, other tweaks. | Click buttons, observe change. |  | April 12th
22 | Working menu, with undo and new, and other options. Undo with 'u' button on keyboard. | Draw shapes, press or hold 'u'. Click file -> new with shapes on drawing panel. |  | April 12th
23 | Fancy text fields, size and font selection. | Set text options with text menu, click text button, draw text. |  | April 14th
24 | Added brush size selection Jspinner. | Select number with bottom right Jspinner. Select brush. Draw. Repeat. |  | April 14th
25 | Added 'spray paint' to fill in empty button. Added texttooltip for confusing fill button. | Select spray paint on side panel, draw on drawing panel. |  | April 15th
| Update UML/Javadoc |  | Ongoing... |  | Not very fun!