## Sheet1
Project name: |  | Team number and members:
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Free drawing with the mouse | Starts the program and see if the drawing follows the mouse | 2008-03-26 | 2008-03-21
2 | color Chooser | check to see if colors and can changed and dynamanically change | 2008-03-27 | 2008-03-21
3 | Custom brushes | Try using pics as a custom brush to see if they work correctly | 2008-03-28 | 2008-03-23
4 | undo Function | Check to see if the undo fucntion removes drawn items form the list | 2008-03-29 | 2008-03-26
5 | Open save and reopen toolbar | Make sure that the function can open and save images and that we can reopen the toolbar if it gets closed while JPaint is running | 2008-03-30 | 2008-03-26
6 | tooltips and Mnemonics for existing tools | Help text and shortcut keys tested for functionality | 2008-03-31 | 2008-03-27
7 | Polygons | check to see if polygons drawing tools work as expected | 2008-04-11
8 | magic wand | in progress | next week? | 10 aprl
9 | paint bucket | see if it can fill a big space with out blowing up | 2008-04-11 | 2008-04-10
10 | spray paint | see if the pixel distribution works | 2008-04-11
11 | rectangles | rectangle previews and draws to the window | 2008-04-11 | 2008-04-10
12 | filled verisons of shapes | the shapes can be fille with the selected color | 2008-04-10 | 2008-04-10
13
14
15